## LOG
PROG280 Final Project Log
Task | Feature | Status | Duration | Description | Comments
Insert screen sharing | Screen share | Started |  | Adding the allowing of screen sharing | Need a meanse of sending to/from server
note for "screen fix" since this computer needed additional details to sync mouse movement
|  |  | 1.5hrs |  | Screen now sends to server.
|  |  | 5min |  | Packet of screenshot now forwards lobby ID, which can be used to sent to all users in a given lobby
found issue in which disconnect is not always broadcasted from the same client connecting/disconnecting
|  |  | 1hr |  | Attempting to fix difference in screen key click (not matching again)

## EXAMPLE
PROG280 Final Project Log - EXAMPLE
Task | Feature | Status | Duration | Description | Comments
Implement transparent image support | Chat | Completed | 30 minutes | Wasn't that hard I found an example on codeproject | 10/10 would not do this again
Add emoji support | Chat | Abandonned | 5 hours | No one even likes emojis | This is a debatable topic but I decided to scrap the feature
Additional TCP connection for sharing screen image | Meeting | In-Progress | ~1 hour so far | An additional connection will be created so the images do not disrupt the chat functionality | Works okay but UDP may have alleviated bandwidth issues
Request control | Remote Control | Not-Started |  | Allow a user to request control from the host PC | Struggling on where to begin this task